## Project Backlog
Story ID	Title	Description	Date Raised	Status	Sprint Completed				Key
PCG-001	Configurable Noise Generation	As a user, the noise generation system should allow for the caller to specify the width and height of the noise to sample from. The number of layers and persitance should also be configurable.	01/01/17		1				Complete
PCG-002	Improve Main Menu	As a developer, the main menu should allow the setting of level generation properties at run time.	01/01/17		1				In Progress
PCG-003	Tileable Heightmap	As a user, I want to be able to be able to create tileable levels, so that when the player leaves one area it seamlessly connects to the next.	06/01/17		1				To do (critical)
PCG-004	Rewrite GA to use difficulty.	As a developer, the current GA fitness test is slow and does not produce interesting results. Instead, the initial population should be randomly created and fitness defined as how closely the level matches the target difficulty.	08/01/17						To do (future)
PCG-005	Test pathing of levels.	As a developer, we should be testing that a path exists to all objectives otherwise the level cannot be completely.	08/01/17
PCG-006	Improve Pathfinding	As a developer, the current implementation of Jump point search can be improved to gain performace.	01/02/17
PCG-007	Redesign use of difficulty	As a user, the current level generation system produces drastically inconsistant results for the same difficulty level.	01/02/17
PCG-008	Level size tied to device size	As a developer, the width and height of the generated level should not be tied to the size of the screen.	01/02/17
PCG-009	Update Camera to PCG-008	As a developer, the camera should be correctly limited to the level after the changes introduced in PCG-008.	01/02/17
PCG-010	Implement PCG-007	As a developer, the new design produced from PCG-007 should be implemented.	05/02/17
PCG-011	Refine fitness function	As a developer, I would like to continue to improve and test the GA's fitness function.	10/02/17
PCG-012	BUG – Multiple game objects can be added to same tile.	During the level generation process there is currently no check to see if a tile is already in use thus allowing multiple game objects to be placed on the same tile.	12/02/17
PCG-013	Integrate Google Play Location Service	As a developer, I need to be able to access the player's location during level generation.	15/02/17
PCG-014	Retrieve local weather	As a developer, I need to be able to retrieve the player's local weather conditions for level generation.	15/02/17
PCG-015	HTTP REST Client	As a developer, I need a to be able to send REST requests for PCG-014	15/02/17
PCG-016	Refactor Android Activity class	As a developer, I need to change the Android activity class to a FragmentActivity to support PCG-013	15/02/17
PCG-017	Use player's context during generation	As the project proposer, the player's context should be used by during the procedural content generation. This will be implemented by using the player's local weather to adjust the level generation.	15/02/17
PCG-018	New tilesets.	As a developer, the level tileset should reflect the user's local weather.	15/02/17
PCG-019	BUG – Heightmap not correctly rendered	There is an error in the tile selection code before rendering the level that stops the full range of tiles from being used.	21/02/17
PCG-020	Return multiple levels	The use of a GA allows for mutliple optimal solutions to be created. This should be exploited.	22/02/17
PCG-021	Add level Selection UI	As a developer, we should allow the user to select the level they want to play from the pool.	22/02/17
PCG-022	Change Fitness function to return populations average fitness.	As a developer, the fitness of the current population should be used to judge when to exit the GA.	22/02/17
PCG-023	Add Loading screen	As a user, a loading screen should be shown when generating the level pool to show the app hasn't crashed.	24/02/17
PCG-024	Add properties file	As a developer, it would be useful to use a java properties file to define default values.	24/02/17
PCG-025	Player Character	As a developer, there should be a animated character the player controls.	24/02/17
PCG-026	Grid Movement	As a developer, there needs to be a system to support smooth grid based movement.	24/02/17
PCG-027	Player Attack	As a developer, the player character should have an attack animation	27/02/17
PCG-028	Collisions	As a developer, movable game entities should collide with obstacles.	27/02/17
PCG-029	Add Gameplay	As a developer, basic gameplay elements should be added. This includes: the player killing enemies, enemies damaging the player, collecting items heals player, UI updates to current game state.	28/02/17
PCG-030	Separate Path finding logic.	As a developer, the path finding logic should not be in the level generation code.	04/03/17
PCG-031	Add basic enemy AI	As a developer, the enemies should attack the player if near.	04/03/17
PCG-032	Enemies should use path finding.	As a developer, the enemies should path find to the player instead of basic vector movement.	04/03/17
PCG-033	Final Report	The final report should be written.	06/03/17
PCG-034	Play testing	As a developer, feedback on the level generation system would be useful. Create a branch from the main code base for a play testing version.	15/03/17
PCG-035	CRITICAL BUG – Fix multidex build issue	An issue with duplicate class files is causing the multidex build stage to fail.	15/03/17
PCG-036	BUG – Fix use of weather in level generation	The use of the weather during level generation was never checked in.	15/03/17

## Sprint 1
Issues	Story points	Day 1	Day 2	Day 3	Day 4	Day 5	Day 6	Day 7	Day 8	Day 9	Day 10	Day 11	Day 12	Day 13	Day 14	Status
PCG-001	3	3	3	0	0	0	0	0	0	0	0
PCG-002	1	1	1	1	1	1	1	1	0	0	0	0	0
PCG-003	3	3	3	3	3	3	0	0	0	0	0	0	0	0
Total Story points	7	7	7	4	4	4	1	1	1	1	0	0	0	0	0

Sprint Start	Sprint End
02/01/17	15/01/17
Burndown
Day
Story Points

## Sprint 2
Issues	Story points	Day 1	Day 2	Day 3	Day 4	Day 5	Day 6	Day 7	Day 8	Day 9	Day 10	Day 11	Day 12	Day 13	Day 14	Progress
PCG-004	13	13	13	8	8	5	3	0	0	0	0	0	0	0	0
PCG-005	13	13	13	13	13	13	13	13	8	8	5	3	0	0	0
Total Story points	26	26	26	21	21	18	16	13	8	8	5	3	0	0	0

Sprint Start	Sprint End
16/01/17	29/01/17
Burndown
Days
Story Points

## Sprint 3
Issues	Story points	Day 1	Day 2	Day 3	Day 4	Day 5	Day 6	Day 7	Day 8	Day 9	Day 10	Day 11	Day 12	Day 13	Day 14	Progress
PCG-006	5	5	1	0	0	0	0	0	0	0	0
PCG-007	3	3	3	0	0	0	0	0	0	0	0
PCG-008	2	2	2	2	2	2	2	2	1
PCG-009	3	3	3	3	3	3	3	3
PCG-010	8	8	15	10	8	8	8	6	6	5	5	3	1	1	0
Total Story points	21	21	24	15	13	13	13	11	11	10	10	8	6	6	4

Sprint Start	Sprint End
30/01/17	12/02/17
Burndown
Day
Story Points

## Sprint 4
Issues	Story points	Day 1	Day 2	Day 3	Day 4	Day 5	Day 6	Day 7	Day 8	Day 9	Day 10	Day 11	Day 12	Day 13	Day 14	Progress
PCG-008	1	1	1	0	0	0	0	0	0	0	0
PCG-009	3	3	1	0	0	0	0	0	0	0	0
PCG-011
PCG-012	2	2	2	2	2	0	0	0	0	0	0	0	0		0
PCG-013	5	5	5	5	5	2	2	2	0	0	0	0	0	0	0
PCG-014	3	3	3	3	3	3	3	3	0	0	0	0	0
PCG-015	2	2	2	2	2	2	2	2	0	0	0	0	0	0	0
PCG-016	2	2	2	2	2	0	0	0	0	0	0	0	0
PCG-017	2	2	2	2	2	2	2	2	0	0	0
PCG-018	3	3	3	3	3	3	3	3	0	0	0
Total Story points	23	23	21	19	19	12	12	12	8	8	5	5	0	0	0

Sprint Start	Sprint End
13/02/17	26/02/17
Burndown
Day
Story Points

## Sprint 5
Issues	Story points	Day 1	Day 2	Day 3	Day 4	Day 5	Day 6	Day 7	Day 8	Day 9	Day 10	Day 11	Day 12	Day 13	Day 14	Progress
PCG-019	1	0	0	0	0	0	0	0	0
PCG-020	2	2	2	0	0	0	0	0	0	0	0
PCG-021	2	2	2	0	0	0	0	0	0	0	0
PCG-022	1	1	1	0	0	0	0	0	0	0	0
PCG-023	3	3	3	3	3	0	0	0	0	0	0	0	0
PCG-024	1	1	1	1	1	0	0	0	0	0	0	0	0
PCG-025	3	3	3	3	3	3	0	0	0	0	0	0	0	0
PCG-026	5	5	5	5	5	5	5	0	0	0	0	0	0	0	0
PCG-027	1	1	1	1	1	1	0	0	0	0	0	0	0	0
PCG-028	1	1	1	1	1	1	0	0	0	0	0	0	0	0
PCG-029	5	5	5	5	5	5	5	5	3	0	0	0	0
PCG-030	1	1	1	1	1	1	1	1	0	0	0
PCG-031	1	1	1	1	1	1	1	1	0	0	0
Total Story points	27	26	26	21	21	17	12	7	7	7	5	2	0	0	0

Sprint Start	Sprint End
27/02/17	12/03/17
Burndown
Day
Story Points

## Sprint 6
Issues	Story points	Day 1	Day 2	Day 3	Day 4	Day 5	Day 6	Day 7	Day 8	Day 9	Day 10	Day 11	Day 12	Day 13	Day 14	Progress
PCG-033	40	40	35	31	28	23	23	23	23	23	23	23	23
PCG-034	3	0	0	3	3	0	0	0	0	0	0	0	0
PCG-035	3	0	0	3	3	3	0	0	0	0	0	0	0	0
PCG-036	1	0	0	1	1	1	0	0	0	0	0	0	0	0
Total Story points	47	40	35	38	35	27	23	23	23	23	23	23	23	23	23

Sprint Start	Sprint End
13/03/17	26/03/17
Burndown
Day
Story Points